## Sheet1
Workflow Timeline
Task | Responsible party | Working period | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun
|  |  | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27
Cover Page & Contents | M | bar: Sat 29 to Sun 30
Executive Summary | Tai | bar: Sat 29 to Sun 30
Introduction | Tai | bar: Tue 1 to Sun 6
Background: Problem/Need Statement | Bank | bar: Sat 29 to Sun 30; Tue 1 to Sun 6
How To Explain A Problem | all team members | bar: Tue 1 to Sun 6
Analysis: | bar: Sat 5 to Sun 13
i. Causes of Problems | M | bar: Sat 5 to Sun 13
ii. Effects of Problems | Tai | bar: Sat 5 to Sun 13
iii. Evaluation of Competitor | Bank | bar: Sat 5 to Sun 13
Solution with Explanation | M, Bank | bar: Tue 15 to Sun 20
Process/Instructions | Tai | bar: Tue 15 to Sun 20
Conclusion | Bank | bar: Tue 15 to Sun 20
Bibliography | M | bar: Tue 22 to Thu 24
Appendix | M | bar: Tue 22 to Thu 24
Rechecking | all team members | bar: Fri 25 to Sun 27
Working period | bar: Sat 29
Deliver draft version | bar: Sat 29
Deliver fianl version | bar: Sat 29
October | bar: Sat 29
November | bar: Sat 29
Finished | bar: Sat 29
In progress | bar: Sat 29